# CAMB Testing Phases & To‑Do Checklist

This checklist is structured as progressive gates. Each phase must be passed before the next one is meaningful. You have already completed Phase 1 and most of Phase 2.

## Phase 0 — Prerequisites (Foundation)

Goal: Ensure CAMB is being used legitimately at all.

- Custom primordial power spectrum injection is supported by CAMB

- Input spectrum defined on valid k‑range (no extrapolation artifacts)

- Background cosmology held fixed (ΛCDM‑like FRW)

- No hidden fitting or parameter tuning

Pass condition: CAMB runs cleanly with your spectrum and produces TT/TE/EE.

## Phase 1 — Numerical Sanity & Stability (COMPLETED)

Goal: Rule out trivial numerical artifacts.

- Vary k‑sampling density → spectra converge

- Vary internal CAMB step sizes → spectra converge

- Increase accuracy settings → diminishing changes

- χ²/dof decreases monotonically with resolution

- RMS fractional residuals ≲ 10⁻³ to ℓ≈3000

- No ringing, aliasing, or blow‑ups

Pass condition: Results stabilize under refinement.

✔ You are here.

## Phase 2 — Resolution Lock‑In (MOSTLY COMPLETE)

Goal: Establish a reproducible “final numerical configuration.”

- Fix ℓ_max (e.g., 3000)

- Fix GenFT parameters (a₂, κ, n_max)

- Confirm residuals no longer change materially

- Save canonical run (BEST_RUN.txt)

- Re‑run after cold restart to ensure reproducibility

Pass condition: Identical results across reruns.

## Phase 3 — CAMB‑Internal Robustness

Goal: Ensure results are not CAMB‑specific quirks.

- Change CAMB integration tolerances independently

- Toggle CAMB approximation flags (where safe)

- Verify lensing on/off does not destabilize spectra

- Confirm no sensitivity to CAMB spline/interp settings

Pass condition: Qualitative agreement across internal modes.

## Phase 4 — Cross‑Code Validation (CRITICAL)

Goal: Prove results are not solver‑dependent.

- Feed identical P(k) into CLASS

- Match background parameters exactly

- Compare TT/TE/EE band‑by‑band

- Quantify CAMB–CLASS differences

Pass condition: Agreement within expected numerical tolerance.

⚠️ Failure here is serious.

## Phase 5 — Controlled Feature Stress Tests

Goal: Demonstrate understanding of failure modes.

- Inject mild oscillatory features into P(k)

- Show coarse k‑sampling breaks convergence

- Increase k‑resolution → convergence restored

- Document thresholds where CAMB fails

Pass condition: You can predict when and why CAMB breaks.

## Phase 6 — Observable Expansion

Goal: Move beyond unlensed TT/TE/EE.

- Lensed TT/TE/EE

- CMB lensing potential C_L^{φφ}

- Matter power spectrum P(k)

- σ₈ sensitivity check

Pass condition: No new instabilities introduced.

## Phase 7 — Likelihood‑Level Testing

Goal: Transition from “numerically sane” to “data‑constrained.”

- Run Planck (or mock) likelihoods

- Report Δχ² relative to ΛCDM baseline

- Identify ℓ‑ranges driving residuals

- Explicitly state: no fitting performed

Pass condition: Honest likelihood comparison available.

## Phase 8 — Documentation & Auditability

Goal: Make results reviewable by others.

- Archive all input spectra

- Archive CAMB configs

- Version‑control code and data

- Write numerical methods appendix

Pass condition: Independent reproduction is possible.

## Phase 9 — Red‑Team Review (Optional but Recommended)

Goal: Try to kill it.

- Feed write‑up to external AI critics

- Simulate hostile referee report

- Address all non‑trivial objections

## Final Completion Criteria

CAMB testing is complete when:

- Numerical convergence is locked

- Cross‑code validation passes

- Failure modes are documented

- Likelihood results exist

- Claims are strictly limited to what was tested

### Guiding Principle

CAMB testing does not prove a theory correct — it proves you are not fooling yourself numerically.